## Sheet1
Human Resource Analytics
Project Planning Roster
| No | Tasks | Assignee | Due Date
| 1 | Check type of variables | Whole team required | 2017-03-10
| 2 | Rename variables for better understanding | Whole team required | 2017-03-10
| 3 | Add a unique identifier for each employee | Whole team required | 2017-03-10
| 4 | Decide on what makes an employee valuable? | Whole team required | 2017-03-10
| 5 | Decide on who all are valuable employees? | Whole team required | 2017-03-10
| 6 | Define premature exit | Whole team required | 2017-03-10
| 7 | Find distribution of each features which are numeric | Whole team required | 2017-03-10
| 8 | Plot box plots for all variables | Nivedita | 2017-03-11
| 9 | Check for missing values in each variable | Nivedita | 2017-03-11
| 10 | Find the ‘mode’ for categorical variables | Nivedita | 2017-03-11
| 11 | Replace missing values with mode for categorical variables | Nivedita | 2017-03-11
| 12 | Find mean and median for numerical variables | Nivedita | 2017-03-11
| 13 | Replace missing values with median for numeric variables | Snehal | 2017-03-12
| 14 | Find descriptive summary statistics for all variables | Snehal | 2017-03-12
| 15 | Find correlations between variables | Snehal | 2017-03-12
| 16 | Plot correlation matrix | Snehal | 2017-03-12
| 17 | Drop variables which are highly correlated | Whole team required | 2017-03-13
| 18 | Implement Mallow’s Cp for feature selection | Naveen | 2017-03-15
| 19 | Implement Forward selection for feature selection | Divya | 2017-03-15
| 20 | Implement backward selection for feature selection | Snehal | 2017-03-15
| 21 | Implement the LASSO for feature selection | Nivedita | 2017-03-15
| 22 | Finalize one of the above method for feature selection for fitting the model | Whole team required | 2017-03-17
| Team weekly meeting |  |  | 2017-03-17
| 23 | Splitting the data into train and test using stratified sampling technique | Nivedita | 2017-03-18
| 24 | Fit a Logistic Regression model (under GLM) with the features selected above on train data | Nivedita | 2017-03-18
| 25 | Check ‘Summary Statistics’ for fitted model | Nivedita | 2017-03-18
| 26 | Plot Fitted Values vs Residuals | Nivedita | 2017-03-18
| 27 | Plot QQ-plot | Nivedita | 2017-03-18
| 28 | Plot Leverage vs Standardized Residuals | Nivedita | 2017-03-18
| 29 | Plot Scale-Location | Nivedita | 2017-03-18
| 30 | Predict values using the GLM model fitted above | Divya | 2017-03-20
| 31 | Create confusion matrix | Divya | 2017-03-20
| 32 | Calculate Accuracy, Precision, Recall from the confusion matrix | Divya | 2017-03-20
| 33 | Plot ROC curve | Divya | 2017-03-20
| 34 | Fit a Decision Tree model with the features selected above on train data | Naveen | 2017-03-22
| 35 | Check ‘Summary Statistics’ for fitted model | Naveen | 2017-03-22
| 36 | Predict the values using the model fitted above | Naveen | 2017-03-22
| 37 | Create confusion matrix | Naveen | 2017-03-22
| 38 | Calculate Accuracy, Precision, Recall from the confusion matrix | Naveen | 2017-03-22
| 39 | Plot ROC curve | Naveen | 2017-03-22
| 40 | Fit a model using the Random Forest algorithm with the features selected above on train data | Snehal | 2017-03-24
| 41 | Check ‘Summary Statistics’ for fitted model | Snehal | 2017-03-24
| 42 | Predict the values using the model fitted above | Snehal | 2017-03-24
| 43 | Create confusion matrix | Snehal | 2017-03-24
| 44 | Calculate Accuracy, Precision, Recall from the confusion matrix | Snehal | 2017-03-24
| 45 | Plot ROC curve | Snehal | 2017-03-24
| Team weekly meeting |  |  | 2017-03-24
| 46 | Fit a model using Gradient Boosting with the features selected above on train data | Nivedita | 2017-03-25
| 47 | Check ‘Summary Statistics’ for fitted model | Nivedita | 2017-03-25
| 48 | Predict values using the GLM model fitted above | Nivedita | 2017-03-25
| 49 | Create confusion matrix | Nivedita | 2017-03-26
| 50 | Calculate Accuracy, Precision, Recall from the confusion matrix | Nivedita | 2017-03-26
| 51 | Plot ROC curve | Nivedita | 2017-03-26
| 52 | Fit a model using SVM algorithm with the features selected above on train data | Naveen | 2017-03-28
| 53 | Check ‘Summary Statistics’ for fitted model | Naveen | 2017-03-28
| 54 | Predict values using the GLM model fitted above | Naveen | 2017-03-28
| 55 | Create confusion matrix | Naveen | 2017-03-29
| 56 | Calculate Accuracy, Precision, Recall from the confusion matrix | Naveen | 2017-03-29
| 57 | Plot ROC curve | Naveen | 2017-03-29
| Team final meeting |  |  | 2017-03-31
| 58 | Implement clustering algorithms as well, so planning to use the K-means for modelling | Divya | 2017-04-01
| 59 | Implement ‘NBClust’ for finding the best number of clusters | Divya | 2017-04-01
| 60 | Categorize employees into their major reason of exit based on clustering algorithm results | Divya | 2017-04-02
| 61 | Based on the above categories suggest measures to retain valuable employees | Divya | 2017-04-02
| 62 | Fit model using the K-Means algorithm with the features selected above on train data | Divya | 2017-04-02
| 63 | Plot the analysis for premature exit of the employee based on above study | Snehal | 2017-04-04
| 64 | Check ‘Summary Statistics’ for fitted model | Snehal | 2017-04-04
| 65 | Predict values using the model fitted above | Snehal | 2017-04-04
| 66 | Create confusion matrix | Snehal | 2017-04-05
| 67 | Calculate Accuracy, Precision, Recall from the confusion matrix | Snehal | 2017-04-05
| 68 | Plot ROC curve | Snehal | 2017-04-05
| 69 | Select an effective model to predict premature exit of employees | Whole team required | 2017-04-07
| 70 | After fitting all these models, we will identify the best model based on ‘Accuracy’. The higher the value the model is the better | Whole team required | 2017-04-07
| Team final meeting |  |  | 2017-04-07